## Ashwin
Sr. No | Date | Description | Action | Target Date | Status | Owner of the Process | Status
1 | 2018-09-07 | Website for zetta using python Language | Tried to make gif images,videos. Searched best contact page. Designed various style of home page. | 30/07/2018 | Pending | Ashwin
2 | 2018-10-07 |  | Slider image designed. Footer designed and formated. Different color used to freez site home page. Contact page designed partialy.
3 | 2018-11-07 |  | Different menu designs are presented for review.
4 | 2018-12-07 |  | Searched, downloaded and designed varities of website menus.
5 | 13/7/2018 |  | New style of sites are customized
6 | 14/7/2018 |  | Logo Modification under progress